## Sheet1
Work Package | Task ID | Task Description | Prerequisites
WP1: Data Pipeline & Hardware Setup | T1 | Procurement and integration of 2nd sEMG Module | None
| T2 | Hardware Debugging & Signal Pre-processing Optimisation | T1
| T3 | Development of Automated Data Annotation Pipeline via visual synchronisation | T2
WP2: Progressive Algorithm Evaluation | T4 | Level 1& 2 tuning: Baseline binary and advanced state classification (SVM, Random Forest) | T3
| T5 | Level 3 tuning: Temporal sequence analysis for continuous gesture recognition (LSTM) | T4
| T6 | Level 4 tuning: Complex intent recognition and fine-grained prediction (CNN) | T5
WP3: System Validation & Deployment | T7 | Kinematic simulation validation (Sim-to-Sim) | T6
| T8 | Physical deployment and tendon-driven actuation testing (Sim-to-Real) | T7
WP4: Report Writing | T9 | Outline finalisation, Introduction and literature review | None
| T10 | Methodology drafting | T3
| T11 | Result analysis, Discussion and Future work | T8
| T12 | Final report content and formatting check | T11

## Project schedule
| Boundary Evaluation of Low-Fidelity sEMG Acquisition for Dexterous Hand Control |  |  |  | Project start: | [7 empty] | 2026-03-30
[5 empty] | Display week: | [7 empty] | 1
Lihao ZHOU
[5 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18
| TASK | START | END | time axis 2026-03-30 to 2026-05-24
 | time axis 2026-03-30 to 2026-05-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
WP1: Data Pipeline & Hardware Seup
| T1 | 2026-03-30 | 2026-04-05 | 7
| T2 | 2026-04-06 | 2026-04-19 | 14
| T3 | 2026-04-20 | 2026-05-03 | 14
WP2: Progressive Algorithm Evaluation
| T4 | 2026-05-27 | 2026-06-07 | 12
| T5 | 2026-06-08 | 2026-06-17 | 10
| T6 | 2026-06-18 | 2026-06-28 | 11
WP3: System Validation & Deployment
| T7 | 2026-06-29 | 2026-07-08 | 10
| T8 | 2026-07-09 | 2026-07-19 | 11
WP4: Thesis Writing
| T9 | 2026-05-04 | 2026-05-26 | 23
| T10 | 2026-05-27 | 2026-06-14 | 19
| T11 | 2026-07-20 | 2026-07-26 | 7
| T12 | 2026-07-27 | 2026-07-30 | 4
Insert new rows ABOVE this one